## Sheet1
Task | Start | Duration
Develop basic simulation | 0 | 2
Development of rules | 1 | 2
Basic layout | 2 | 2
Advanced layout | 4 | 2
Logic implementation | 5 | 4
Text-based debugging | 8 | 1
AI development | 9 | 2
AI debugging | 10 | 1
Graphics development | 11 | 2
Graphics debugging | 12 | 1
Sounds development | 13 | 2
Sounds debugging | 13 | 1
Complete engine debugging | 14 | 2
Preprogram components | 16 | 3
Add graphics | 19 | 2
Add sounds | 19 | 1
Add GUI | 20 | 2
Alpha Testing | 20 | 2
Beta Testing | 22 | 2
Post-Release debugging | 24 | 1